## WBS Structure
S/N | Phase | Activity | Quantity | Rate | Amount | Remarks | Assigned To | Status
1.1 | Phase 1: Planning & Design | Site Survey and Soil Investigation | 1 | 150000 | 150000 | Critical path item | Surveying Team | Completed
1.2 | Phase 1: Planning & Design | Architectural Drawings & Structural Design | 1 | 500000 | 500000 | Awaiting final approval | Arch. John Doe | In Progress
1.3 | Phase 1: Planning & Design | Permits and Regulatory Approvals | 1 | 250000 | 250000 | Local municipal council | Legal Liaison | Pending
2.1 | Phase 2: Foundation & Substructure | Site Clearing and Excavation | 350 | 1200 | 420000 | Measured in cubic meters | Excavation Subcontractor | Not Started
2.2 | Phase 2: Foundation & Substructure | Reinforcement Steel (Rebar) Installation | 5 | 95000 | 475000 | Tons of steel reinforcement | Ironworks Corp | Not Started
2.3 | Phase 2: Foundation & Substructure | Concrete Pouring (Footings & Slab) | 80 | 4500 | 360000 | Grade M25 Concrete | Concrete ReadyMix | Not Started
3.1 | Phase 3: Superstructure & Framing | Brickwork and Partition Walls | 1200 | 450 | 540000 | Hollow concrete blocks | Masonry Team | Not Started
3.2 | Phase 3: Superstructure & Framing | Roof Truss Fabrication & Installation | 1 | 680000 | 680000 | Treated hardwood framing | Roofing Specialist | Not Started
3.3 | Phase 3: Superstructure & Framing | Roofing Sheet Installation | 280 | 1800 | 504000 | Aluminium roofing sheets | Roofing Specialist | Not Started
4.1 | Phase 4: MEP & Finishes | Electrical Piping & Wiring First Fix | 1 | 300000 | 300000 | Conduit layout | Sparky & Partners | Not Started
4.2 | Phase 4: MEP & Finishes | Plumbing Pipe Laying & Drainage Connect | 1 | 280000 | 280000 | PPR pipework | FlowRight Plumbers | Not Started
4.3 | Phase 4: MEP & Finishes | Wall Plastering and Screeding | 450 | 800 | 360000 | Internal and external wall areas | Plastering Crew | Not Started